STC – Mid Value Domestic On-site Works

| Bidder Name | : | [insert name of the bidder] |
| --- | --- | --- |
| Offer Reference Number and Date | : | [insert details of the offer] |
| Offer validity | : | [Sixty (60)] days from the date of submission of the final offer. |
| Note to bidder: - The terms and conditions specified herein, including any negotiated positions, shall be incorporated in the Service Order that will be issued to the successful bidder. For the purpose of this enquiry, all references to ‘Service Order’ herein shall be read as references to this ‘STC’. - The terms and conditions applicable to the SO Documents, other than the commercial terms and conditions set out herein (including any negotiated positions) or any schedules that may be attached, shall be as per the GTC. - Please note that it is mandatory for the bidder to insert the applicable response (from options (a) or (b) below) in the ‘Bidder Response’ column for each line item in the table below: - Agreed; or - Not agreed (in such case, bidder to provide relevant deviation). |  |  |

| Sr. No. | Particulars | Employer's Terms and Conditions | Bidder Response |
| --- | --- | --- | --- |
|  | Scope of Work | Supply and installation of OPGW Cable and its hardware fittings for 765kV Sasan – Vindhyachal Transmission Line in the state of Madhya Pradesh | [Bidder to insert response as per Note (3) above] |
|  | Effective Date | The Effective Date shall mean the date of issuance of the Order or from the NTP given by the Employer to the Contractor. | [Bidder to insert response as per Note (3) above] |
|  | Site | The Contractor shall perform the Works at Sasan Singrauli, MP,India, 486886 | [Bidder to insert response as per Note (3) above] |
|  | Completion Schedule | Supply: All the Goods covered under the PO shall be delivered (On FOR Site basis) at site within 4 weeks from the date of PO. Service: The Contractor shall perform the Service and achieve Completion within 45 days from the date notified by the Owner as the commencement date, which is inclusive of mobilisation period. | [Bidder to insert response as per Note (3) above] |
|  | Basic Price | 5.1 The Basic Price shall be as specified in the Price Schedule set out in ‘Annexure I: Price Schedule’ and shall be payable on a BOQ basis. The Basic Price shall be inclusive of applicable Taxes (except GST), labour and other statutory charges, gratuity amounts, cost of materials, consumables, tools and tackles, insurance charges, margin, overheads, charges for Bank Guarantees and other costs associated with the performance of the Scope of Work. | [Bidder to insert the Basic Price in the Price Schedule] |
|  | SO Price | 5.2 The SO Price shall be as specified in the Price Schedule set out in ‘Annexure I: Price Schedule’, which shall be inclusive of GST. | [Bidder to insert the Total Price payable in the Price Schedule] |
|  | Taxes | GST shall be paid at actuals, as per the rates specified in the Price Schedule set out in ‘Annexure I: Price Schedule’. | [Bidder to insert the applicable GST rates in the Price Schedule] |
|  | Payment Terms | Supply: 100% of Contract Price with applicable GST shall be paid on Pro-rata basis within 30 days through RTGS after receipt of material at site & submission of following documents. a. Order Acceptance Copy b. Invoice: 1 set of original + 2 set of copies. c. Copy of applicable e-way Bill. d. LR/GR/RR (if applicable): 3 set of copies. e. Packing List/Delivery Challan: 3 set of copies. f. Test Certificates, wherever applicable: 3 set of copies. g. MDCC issued by the Buyer prior to dispatch: 3 set of copies. h. Joint verification report of material. Final Payment shall be made after adjusting the amounts due to the Buyer by Seller including applicable LD, if any, the previous payments made and statutory deductions, if any. All other sub clauses of clause No. 5 of the GCC shall remain unaltered. Service : Ninety Percent (90%) of the Contract Price shall be paid on pro-rata basis within Thirty (30) days from the date of receipt of following documents from the Contractor: a. Running Account Bill / invoice: one (1) set of original and two (2) sets of copies. b. Contract Performance Bank Guarantee@10% of Basic Price c. Any document evidencing acceptance of the SO Documents. d. Copy of insurance policies to be procured by the Contractor; and e. Copy of statutory registrations as required for performance of the Services under the SO Documents. Balance Ten Percent (10%) of the Contract Price shall be paid after completion of work but with Thirty (30) days from the date of receipt of following documents from the contractor: a. Performance Bank Guarantee@10% of the Basic Price. b. Certificate issued by the Employer for satisfactory Completion of the Work. c. Reconciliation statement of Free Issue Materials Note: If the Contractor fails to provide a CPBG cum PBG of 10% then equivalent amount of Contract Price will be kept under hold till DLP. | [Bidder to insert response as per Note (3) above] |
|  | 8.1 Delay Liquidated Damages | Supply and Service: In the event of delay in delivery/ completion of the works/ facilities (Lot-wise) as specified under the scope of the Contract due to the reasons attributable to the Seller, the Seller shall be liable to pay LD @ 0.5% of the Contract Price for the lot which is delayed for each completed week of delay or part thereof subject to a maximum of 5% of the Contract Price for respective Lot. LD to be settled at the time of release of lot-wise retention amount. GST shall be applicable on LD amount and Seller is liable to pay the same. | [Bidder to insert response as per Note (3) above] |
|  | 8.2 Shortfall Liquidated Damages | NA | [Bidder to insert response as per Note (3) above] |
|  | 8.3 Overall cap for liquidated damages | NA | [Bidder to insert response as per Note (3) above] |
|  | 8.4 Other liquidated damages | NA | [Bidder to insert response as per Note (3) above] |
|  | 9.1 Advance Payment Bank Guarantee | NA | [Bidder to insert response as per Note (3) above] |
|  | 9.2 Contract Performance Bank Guarantee | NA | [Bidder to insert response as per Note (3) above] |
|  | 9.3 Performance Bank Guarantee | NA | [Bidder to insert response as per Note (3) above] |
|  | 9.4 Contract Performance cum Performance Bank Guarantee | Supply and Service: Contract Performance cum Performance Bank Guarantee (CPBG cum PBG): Within fifteen (15) days from the Effective Date, the Seller shall submit the Contract Performance cum Performance Bank Guarantee, in the form provided along with the Purchase Order, for an amount equal to 10% of the Basic Price, which shall remain valid and effective till the expiry of the Defect Liability Period, with a claim period of thirty (30) days from the expiry of the Defect Liability Period. Contractor to submit the CPBG cum PBG within 30 days from the date of release of Contract. In case of non-establishment of BG, the equivalent amount shall be kept on Hold till the DLP. | [Bidder to insert response as per Note (3) above] |
|  | Defect Liability Period | Supply: The Defect Liability Period shall be 12 months from the date of successful Commissioning or 18 months from the date of receipt of Goods at the Delivery Point, whichever is earlier. Service: The Defect Liability Period shall be for a period of Twelve (12) months from the date of Completion of work. | [Bidder to insert response as per Note (3) above] |
|  | MSME Status | The Contractor is registered as a [micro/small/medium] enterprise under the Micro, Small and Medium Enterprises Development Act, 2006 and the rules and regulations made thereunder. The Contractor shall furnish documentary evidence with respect to its status as a [micro/small/medium] enterprise. [Retain as may be applicable] [Note: If the Contractor is not a micro, small or medium enterprise, mention ‘Not Applicable’.] | [Bidder to specify if it is registered as an MSME and if yes, Bidder to furnish the MSME certificate.] |
|  | Specific Agreed Terms | Free Issue Material: NA Utilities and Facilities: NA Insurance: Contractor shall take all kinds of applicable insurance required to execute the subject Contract. Contractor should insure their employees and keep insure till the Completion of this Contract/issuance of taking over Certificate. Copy of such Policy shall be submitted to Owner. - Unit rates are firm till the completion of the complete scope of work. Payment to the Seller shall be released based on the actual supplied/executed quantities. - Seller to comply with Buyer technical specification for all equipment/ items required for completion of the package. - Seller to follow approved sub-vendor list, SQP and other QA documents etc. as per Buyer specifications. - The Seller will perform the Services in a manner that gives appropriate regard to the protection of the natural environment. - The Seller will comply with all Statutory & Regulatory requirements and codes of practices relating to the products and services being offered as may be relevant. - MSDS to be sent for all hazardous chemicals & gases along with consignment. - Considering the market scenario, Seller has to take all necessary actions at their end to ensure execution of the Contract on Firm price basis. - In case on FIM contractor shall arrange transportation of material from employer designated store to site location at their own cost. - The Contractor shall fulfil the OHS requirement of the Owner in totality. - Contractor equipment's/ T&P shall be calibrated. - Contractor shall ensure to deploy a Safety Supervisor at site, who shall be responsible to ensure safety implementation at site. - Mandatory PPEs (Safety Helmet, Safety shoes, Safety Goggles, Safety Gloves and Reflective Jacket) and activity specific PPEs should be available for each personnel working at site. - Apart from mandatory PPEs, Contractor shall provide all job specific PPEs and safety equipment adequately. - Compliance with OHS manual must be ensured and please give more consideration to Appendix no. 02 Safety violation penalties. - Lodging, boarding, local conveyance & transportation of Contractor workmen shall be in Contractor's Scope. - Contractor to submit the medical fitness report of their manpower before execution of work at site. - Prior to start the work, contractor shall submit the Emergency Preparedness Plan. | [Bidder to insert response as per Note (3) above] |

| Details of Bidder's Authorised Signatory |  |  |
| --- | --- | --- |
| Signature | : | _________________________ |
| Name | : | _________________________ |
| Designation | : | _________________________ |
| Stamp | : |  |